## Project_Overview
Field | Value
Project Name | Cloud Migration Implementation
Project Manager | Edgar
Project Start Date | 2026-01-07
Expected End Date | 15/08/2026
Project Status | In Progress
Overall Risk Level | Medium

## Task_Tracker
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Column1
T1 | Digitise paper records | Data Team | 2026-01-07 | 2026-07-07 | In Progress
T2 | Configure cloud storage | IT Team | 2026-05-07 | 2026-12-07 | Pending
T3 | Migrate digital records | IT Team | 13/07/2026 | 20/07/2026 | Pending
T4 | Staff training | HR Team | 25/07/2026 | 30/07/2026 | Pending

## Risk_Register
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Risk ID | Risk Description | Likelihood | Impact | Risk Level | Mitigation
R1 | Data loss during migration | Medium | High | High | Backup data before migration
R2 | Staff resistance | Medium | Medium | Medium | Provide training
R3 | Cloud security vulnerability | Low | High | Medium | Implement access controls

## Issue_Log
Issue ID | Issue Description | Reported By | Date | Status | Resolution
I1 | Delay in scanning documents | Data Team | 2026-04-07 | Open | Allocate additional staff
I2 | Cloud storage configuration error | IT Team | 2026-10-07 | In Progress | IT troubleshooting

## Milestones
Milestone | Target Date | Status
Project Planning Completed | 2026-05-07 | Completed
Cloud System Setup | 2026-12-07 | Pending
Data Migration | 20/07/2026 | Pending
Staff Training | 30/07/2026 | Pending